## Issues review
ID | Title | State | Priority | Self-contained ESPD | Impact on data flow | Impact on data model | Comments
1 | Weighting | Closed |  | √ | √ | √ | Please find the details of the final decision in https://github.com/ESPD/ESPD-EDM/wiki/4.-Weighting
2 | Change cardinality of req inside req-groups from 1...* to 0...* | Closed |  | √ | √ | √
3 | Add explanation what will happen if EO selects YES / NO | Closed |  |  |  |  | Per each pair YES/NO a tooltip explaining the behaviour of the components depending of the selected answer should be shown in the user graphic interface.
4 | Part III: Exclusion grounds, D: Purely national exclusion grounds | Pending closure |  | √ | √ | √
5 | Part IV: Selection criteria, ɑ: Global indication for all selection criteria | Closed
6 | Part IV: Selection criteria, A: Suitability | Pending discussion | Medium | √ | √ | √ | Examples required
7 | Part IV: Selection criteria, A: Suitability - For service contracts | Pending closure |  | √ | √
8 | Part IV, Section B (General yearly turnover) | Closed |  | √ | √ | √ | Please find the details of the final decision in https://github.com/ESPD/ESPD-EDM/wiki/1.-General-Turnover
9 | Part IV, Section B (Average yearly turnover) | Closed |  | √ | √ | √
10 | Part IV, Section B (Specific yearly turnover) | Closed |  | √ | √ | √ | Please find the details of the final decision in https://github.com/ESPD/ESPD-EDM/wiki/2.-Specific-Turnover
11 | Part IV, Section B (Specific average turnover) | Closed |  | √ | √ | √ | Please find the details of the final decision in https://github.com/ESPD/ESPD-EDM/wiki/2.-Specific-Turnover
12 | Part IV, Section B (Financial ratio) | Closed |  | √ | √ | √ | Please find the details of the final decision in https://github.com/ESPD/ESPD-EDM/wiki/3.-Financial-Ratios
13 | Part IV, Section B (Professional risk indemnity insurance) | Pending discussion | Medium | √ | ? | ? | Examples required
14 | Part IV, Section B (Other economic or financial requirements) | Pending discussion | Medium | √ | ? | ? | Examples required
15 | Part IV: Selection criteria, C: Technical and professional ability - For works contracts | Pending closure |  | √ | √
16 | Part IV: Selection criteria, C: Technical and professional ability - For supply contracts | Pending closure |  | √ | √
17 | Part IV, Section C (For service contracts: performance of services of the specified type) | Closed |  | √ | √ |  | Unified with issue #7
18 | Part IV: Selection criteria, C: Technical and professional ability - Specific requirements | Pending discussion | Medium |  | ? | ? | Examples required
19 | Part IV, Section C (For works contracts: technicians or technical bodies to carry out the work) | Closed |  | √ | √ |  | Unified with issue #15
20 | Part IV, Section C (Technical facilities and measures for ensuring quality) | Closed |  | √ | ? | ? | Unified with issue #18
21 | Part IV, Section C (Study and research facilities) | Closed |  | √ | ? | ? | Unified with issue #18
22 | Part IV, Section C (Supply chain management) | Closed |  | √ | ? | ? | Unified with issue #18
23 | Part IV, Section C (Allowance of checks) | Closed |  | √ | ? | ? | Unified with issue #18
24 | Part IV, Section C (Educational and professional qualifications) | Closed |  | √ | ? | ? | Unified with issue #18
25 | Part IV, Section C (Environmental management measures) | Closed |  | √ | ? | ? | Unified with issue #18
26 | Part IV, Section C (Number of managerial staff) | Closed |  | √ | ? | ? | Unified with issue #18
27 | Part IV, Section C (Average annual manpower) | Closed |  | √ | ? | ? | Unified with issue #18
28 | Part IV, Section C (Tools, plant or technical equipment) | Closed |  | √ | ? | ? | Unified with issue #18
29 | Part IV: Selection criteria, C: Technical and professional ability - Subcontracting questions | Pending discussion | Low |  | √
30 | Part IV, Section C (For supply contracts: samples, descriptions or photographs without certification of authenticity) | Closed |  | √ | √ |  | Unified with issues #16 and #18
31 | Part IV, Section C (For supply contracts: samples, descriptions or photographs with certification of authenticity) | Closed |  | √ | √ |  | Unified with issues #16 and #18
32 | Part IV, Section C (For supply contracts: certificates by quality control institutes) | Closed |  | √ | √ |  | Unified with issues #16 and #18
33 | Part IV: Selection criteria, D: Quality assurance schemes and environmental management standards - Specific requirements | Pending discussion | Medium | √ | √ |  | Examples required
34 | Part IV, Section D (Certificates by independent bodies about environmental management systems or standards) | Closed |  | √ | √ |  | Unified with issue #33
35 | Part VI: Concluding statements | Pending discussion | Low
36 | ESPD alignment with TED notices | Pending discussion | High | √ | √ | √
37 | Update the data model to version 1.0.2 | Closed
38 | Defining attributes in the adoc main document | Technical |  |  |  |  | Pending.
39 | Field for EOs role | Closed |  |  |  |  | Duplicate. Please see issue #57. New codelist EO role.
40 | ERRORS in current ESPD: average yearly turnover and average and specific average turnover | Closed |  | √ |  |  | Solved
41 | Transformation from old XML to new XML via XSLT | Technical |  |  |  |  | Cannot be possible until current model is totally specified.
42 | Wrong reference to code list in cbc: Amount | Technical
43 | Link between ESPD and e-Certis: the information displayed is based on the country of the CA, or on the country of the EO? | Pending discussion | High
44 | Part IV: Selection criteria, B: Economic and financial standing, TURNOVERS | Closed |  | √ |  |  | Please find the details of the final decision in https://github.com/ESPD/ESPD-EDM/wiki/1.-General-Turnover and https://github.com/ESPD/ESPD-EDM/wiki/2.-Specific-Turnover
45 | Codelist for CustomizationID contains wrong values | Technical |  |  |  |  | This error comes from CEN/BII. Solution in progress.
46 | Financial Ratios | Closed |  | √ | √ | √ | Please find the details of the final decision in https://github.com/ESPD/ESPD-EDM/wiki/3.-Financial-Ratios
47 | Pre-qualification systems and classification of Eos | Pending final decision | High | √ | √
48 | Quality assurance | Closed |  | √ | √ |  | Unified with issue #33
49 | Procurement procedure can be divided into Lots | Closed |  |  | √ | √ | Please see issue https://github.com/ESPD/ESPD-EDM/issues/55
50 | Diferent qualification criteria for subcontractors | Closed |  |  |  |  | See please issue https://github.com/ESPD/ESPD-EDM/issues/57
51 | ESPD inside Finland’s eTendering system | Closed
52 | Part II, Section C - Consortium | Closed
53 | ResponseDataType should be an element of Requirement not an attribute | Closed |  |  |  |  | This is aligned to UBL2.2 and is very technical. The impact is on the software applications but it is minimal.
54 | Part III, Section B - Payments of Taxes | Pending final decision | Medium | √ | √
55 | Criterion dependencies (Lots) | Pending final decision | SuperHigh |  | √ | √
56 | Regulated ESPD vs Self-contained ESPD | Pending final decision | Medium-Low |  |  | √
57 | Elements for the identification of a Consortium (EO roles) | Closed |  |  |  |  | Please find the details of the final decision in https://github.com/ESPD/ESPD-EDM/wiki/5.-EO-roles
58 | Evidence Issuer is separate requirement; Should be inside <cev:Evidence> | Technical |  |  |  | √ | Work in progress
59 | ESPD inside eTendering - Finland | Closed |  |  |  |  | Specific information about EO roles management in Finland. For global information regarding EO roles, please see issue #57.
60 | Conformance testing issue with <cbc:CustomizationID> for ESPD Request | Closed |  |  |  |  | Unified with issue #45
61 | Bug in <cac:AdditionalDocumentReference> used for “Information concerning the procurement procedure” (document type code: TED_CN) | Technical |  |  |  |  | Work in progress
62 | Issues with <cac:AdditionalDocumentReference> used in ESPD Response for referring to ESPD Request document (document type code: ESPD_REQUEST) | Technical |  |  |  |  | Work in progress
63 | ESPD XML Schema version incosistencies | Technical |  |  |  |  | We are working in a new versioning model
64 | EO roles | Closed |  |  |  |  | Duplicate. Please see issue #57.
65 | Part IV, Section C (Trade Secret) | Pending final decision | Medium | √ |  | √
66 | Semantic error in ESPD XML Schema: Usage of XML element […].Postbox for postcode (zipcode) | Closed |  |  |  |  | Reported to UBL2.2
67 | Part IV, Section C (References) | Pending final decision | Medium | √
68 | Part I, section "Information about publication" | Closed | Medium